## Open POA&M Items
| POAM ID | Controls | Weakness Name | Weakness Description | Weakness Detector Source | Weakness Source Identifier | Asset Identifier | Point of Contact | Resources Required | Remediation Plan | Original Detection Date | Scheduled Completion Date | Status Date | Vendor Dependency | Last Vendor Check-in Date | Vendor Dependent Product Name | Original Risk Rating | Adjusted Risk Rating | Risk Adjustment | False Positive | Operational Requirement | Deviation Rationale | Supporting Documents | Comments | Binding Operational Directive 22-01 tracking | Binding Operational Directive 22-01 Due Date | CVE
Guidance | Assign a unique identifier to each POA&M item. This can be in any format or naming convention that produces uniqueness. NOTE: During initial and annual assessments, assessors are instructed to use the CSP-established schema to assign a unique identifier (ID) to each RET item. | Enter the 800-53 control or controls that is/are affected by the weakness. If multiple controls are affected, separate them with commas. | Enter a short description of the weakness. For scan-related vulnerabilities, use the name provided by the scanner. | Enter a full description of the weakness and other relevant information. Security weaknesses must be accurately described so that they can be understood by the CSP and Authorizing Official (AO). If a test was performed using a tool/scanner, use the description provided by the tool/scanner. | Enter the scanner name or other source that detected the weakness. | For scan-related vulnerabilities, include the vulnerability identifier provided by the scanner (plugin ID). Otherwise, leave this field blank. Do NOT enter N/A or None. | Enter the corresponding unique asset ID specified in the Integrated Inventory Workbook (IIW). This is a unique string associated with the asset; it could be an IP address or any arbitrary naming scheme. Include the complete identifier name (no short hand). If multiple assets are affected, separate each by a new line (Alt+Enter). | Person responsible for resolving the weakness. | If needed, specify additional resources required resolve the weakness. | Describe the plan to resolve the weakness, especially if it cannot be fully remediated within the required timeframe. Provide enough detail to help agency customers understand the actions required, why more time is needed, and when the weakness will be fully remediated. | Enter the date the weakness was first identified (also known as the Discovery Date). This date never changes. | The scheduled completion date is automatically calculated based on the original detection date and risk rating. Do not modify this date. Note changes to the remediation plan and timeline in the Remediation Plan column. | Enter the date this POA&M item was last changed or closed. NOTE: Closed POA&Ms are moved to the Closed POA&M Items tab. Simply cut the entire row and paste it in the Closed POA&M Items tab. | If remediation is dependent on a downstream vendor, enter Yes. Otherwise, enter No. | Enter the date of last vendor check-in, if applicable. | Enter the name of the vendor. If Vendor Dependency is Yes, this field must be populated. If Vendor Dependency is No, leave this field blank. Do NOT enter N/A or None. | For scan-related vulnerabilities, enter the original risk rating from the scanner. For non-scan weaknesses, enter the risk rating provided by the assessor or determined through the risk analysis (i.e., likelihood/impact). | Enter the adjusted risk rating if applicable. Otherwise, leave this field blank. Do NOT enter N/A or None. | If there is no risk adjustment (RA), select No from the drop-down. If the RA is pending agency approval, select Pending. If the RA has been approved, select Yes. | A false positive (FP) occurs when a weakness is identified that does not actually exist on the system. This happens from time-to-time with scanning tools. If the weakness is not a FP, select No from the drop-down. If the FP is pending agency approval, select Pending. If the FP has been approved, select Yes and move the POA&M item to the Closed tab. | An operational requirement (OR) occurs when there is a weakness in the system that cannot be corrected without impacting the full operation of the system. If the weakness is not considered an OR, select No from the drop-down. If the OR is pending agency approval, select Pending. If the OR has been approved, select Yes. | Explain the rationale for a risk adjustment or an operational requirement, including a description of any mitigating factors or compensating controls that could downgrade the likelihood or risk exposure. Also indicate whether the affected component(s) is/are internally or externally facing. If a RA or OR does not exist for the weakness, leave this field blank. Do NOT enter N/A or None. | List any supporting documents that are associated with this item (e.g. evidence of remediation,evidence of vendor dependency, etc) | To ensure a complete understanding of the weakness, enter additional information not specified in other columns as appropriate. Otherwise, leave this field blank. Do NOT enter N/A or None. | Is this vulnerability is listed among the CISA Known Exploited Vulnerability Catalog (https://www.cisa.gov/known-exploited-vulnerabilities-catalog) | If this vulnerability is listed among the CISA Known Exploited Vulnerability Catalog (https://www.cisa.gov/known-exploited-vulnerabilities-catalog) include the due date given by CISA for this vulnerability. Otherwise, leave this field blank. Do NOT enter N/A or None. | The associated CVE numbers for this vulnerability, if applicable.
Examples | VS-001-AC(2) PT-204-SR(2) | RA-5, SC-13, IR-3 | Red Hat Update for glibc security (RHSA-2021:4358) Elevated User Privileges | The remote host contains one or more unsupported versions of Python. Lack of support implies that no new security patches for the product will be released by the vendor. As a result, it is likely to contain security vulnerabilities. | <name of> scanner, manual testing, penetration testing | 19506 | 172.246.15.3 (80/TCP) http://vuln.gov/queries 172.246.16.17 (80/TCP) | John Doe - Example CSP |  | Will be resolved during <date> patching cycle. OR Migrate to new technical solution. Planned milestones are: 1) Milestone 1 2) Milestone 2 3) …... | 2024-11-11 | 2014-08-03 | 2024-12-11 | Yes or No | 2014-08-05 | "Vendor XYZ" or leave blank | Low, Moderate, High, Critical | Low, Moderate, High, or leave blank | Yes | No | Pending | Rationale description or leave blank | File name and location | Additional comments or leave blank | Yes or leave blank | 2025-08-05 | CVE-1234-1234
Mandatory or Situational | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Situational | Mandatory | Mandatory | Situational | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Situational | Situational | Mandatory | Situational | Situational | Situational | Situational | Situational | Situational | Situational | Situational | Situational | Situational